## Sheet1
RESPONSIBILITY MATRIX
ROLE/DATE | Feb 6th - 17th | Feb 20th - 3rd Mar | Mar 6th - 10th | Mar 13th - 17th | Mar 20th - 24th | Mar 27th - 31st | April 17th - 21st | April 24th - 28th
Group Leader | Asser | Abdulrahman | Asser | Yousef | Meshina | Taha | Yousef | Asser
Programmer | Abd/Asser | Asser / Taha | Mesh/ Yousef | Asser | Yousef / Abd | Asser/ Yousef | Abd/ Mesh | Taha / Asser
Researcher | Taha/ Meshina | Abd / Yousef | Abdulrahman | Meshina | Asser | Abdulrahman | Asser | Abd/ Yousef
Documentor | Yousef | Meshina | Taha | Abdulrahman | Taha | Meshina | Taha | Meshina
PROJECT TITILE: Object detection for an autonomous race vehicle
[9 empty] | Task Commencing Feb 6th, 2023 | Feb | March | April | May | Dependencies | Resources
Planning
[9 empty] | 1. Define Project scope, requirements and goals |  |  |  |  | None
[9 empty] | 2. Create project plan |  |  |  |  | Define project scope, requirements, goals
[9 empty] | Research and Development |  |  |  |  | Create project plan
[9 empty] | 1. Conduct literature review |  |  |  |  | None
[9 empty] | 2. Research existing object detection algorithms |  |  |  |  | Conduct literature review
[9 empty] | 3. Prototype object detection |  |  |  |  | Research existing object detection algs
[9 empty] | Implementation |  |  |  |  | Prototype object detection
[9 empty] | 1.Develop Object detection system |  |  |  |  | None
[9 empty] | 2. Integrate with vehicle software |  |  |  |  | Develop object detection system
[9 empty] | 3. Testing & Evaluation |  |  |  |  | Integrate your vehicle with software
[9 empty] | 4. Conduct system testing |  |  |  |  | None
[9 empty] | 5. Analyze test results and identify improvements |  |  |  |  | Conduct system testing