## Sheet1
Systems Development Coursework Minutes
Yousef Ali 22002656, Asser Aldardiri (21065616), Taha Seghayer (21065689), Meshina Ushie (22039488), Abdulrahman Ali (21065685)
(Meeting 1) |  |  |  | Topics Discussed | Group Roles
Participants | Location | Time | Date | We decided on a topic and landed on Object detection for autonomous race vehicles | Asser | Group Leader / Programmer
|  |  |  | We also created a discord server for when we want to meet over the weekend | Taha | Reasearcher
Yousef | FR campus, N Block | 4:00PM - 6:00PM | 6 Feb, 2023 | Laid the stages of the project. | Meshina | Reasearcher
Asser | FR campus, N Block | 4:00PM - 6:00PM | 6 Feb, 2023 |  | Abdulrahman | Programmer
Meshina | FR campus, N Block | 4:00PM - 6:00PM | 6 Feb, 2023 |  | Yousef | Documentor
Abdulrahman | FR campus, N Block | 4:00PM - 6:00PM | 6 Feb, 2023
Taha | FR campus, N Block | 4:00PM - 6:00PM | 6 Feb, 2023
(Meeting 2) |  |  |  | Topics Discussed | Group Roles
Participants | Location | Time | Date | Set targets for the project, shared and explained topics to go over that are reqiured for the | Asser | Group Leader / Programmer
|  |  |  | development of the program. | Taha | Reasearcher
Yousef | Discord Meeting | 7:00 PM - 8:00 PM | 7 Feb, 2023 | Created a repo link and pushed some files onto it | Meshina | Reasearcher
Asser | Discord Meeting | 7:00 PM - 8:00 PM | 7 Feb, 2023 |  | Abdulrahman | Programmer
Meshina | Discord Meeting | 7:00 PM - 8:00 PM | 7 Feb, 2023 |  | Yousef | Documentor
Abdulrahman | Discord Meeting | 7:00 PM - 8:00 PM | 7 Feb, 2023
Taha | Discord Meeting | 7:00 PM - 8:00 PM | 7 Feb, 2023
(Meeting 3) |  |  |  | Topics Discussed | Group Roles
Participants | Location | Time | Date | Asser assigned the team different tasks to complete till our next practical lesson. | Asser | Group Leader / Programmer
|  |  |  | Drafted up a report and a Aims and objectives document. | Taha | Reasearcher
Yousef | FR campus, Q Block | 12:00 PM - 3:00PM | 9 Feb, 2023 | We managed to get our program to work with a 47 % accuracy | Meshina | Reasearcher
Asser | FR campus, Q Block | 12:00 PM - 3:00PM | 9 Feb, 2023 | Taha was assigned to go over and help with the code | Abdulrahman | Programmer
Meshina | FR campus, Q Block | 12:00 PM - 3:00PM | 9 Feb, 2023 | Meshina and Abdulrahman were assigned to research other algorithms to make sure Yolo is | Yousef | Documentor
Abdulrahman | FR campus, Q Block | 12:00 PM - 3:00PM | 9 Feb, 2023 | the best way to go.
Taha | FR campus, Q Block | 12:00 PM - 3:00PM | 9 Feb, 2023 | Yousef was assigned to do more research on the topic and improve the report
(Meeting 4) |  |  |  | Topics Discussed | Group Roles
Participants | Location | Time | Date | Changed group roles | Asser | Programmer
|  |  |  | Since we changed group roles we had to finish up previous ongoing work and help new role | Taha | Programmer
Yousef | FR campus, N Block | 3:15 PM - 6:20PM | 20 Feb,2023 | holders understand what has been done so far | Meshina | Documentor
Asser | FR campus, N Block | 3:15 PM - 6:20PM | 20 Feb,2023 | New tasks were assigned to the programmers and Researchs | Abdulrahman | Group Leader / Research
Meshina | FR campus, N Block | 3:15 PM - 6:20PM | 20 Feb,2023 | We changed to SSD instead of YOLO | Yousef | Research
Abdulrahman | FR campus, N Block | 3:15 PM - 6:20PM | 20 Feb,2023
Taha | FR campus, N Block | 3:15 PM - 6:20PM | 20 Feb,2023
[5 empty] | Group Roles |  | Tasks Achieved
(Meeting 5) |  |  |  | Topics Discussed | Asser | Programmer | Asser | Task achieved
Participants | Location | Time | Date | we attempted to run our program but it crashed the laptop from its size, there is too much | Taha | Programmer | Taha | Task achieved
|  |  |  | data to process and our laptops cant handle it. | Meshina | Documentor | Meshina | Task achieved
Yousef | FR campus, N Block | 9:00 AM - 12:00 PM | 23 Feb,2023 | Meshina made progess with the report and the current word count is 1200 words. Task is getting it up to 1500 | Abdulrahman | Group Leader / Research | Abdulrahman | Task achieved
Asser | FR campus, N Block | 9:00 AM - 12:00 PM | 23 Feb,2023 | Researchs task was to do research for the literature review | Yousef | Research | Yousef | Task achieved
Meshina | FR campus, N Block | 9:00 AM - 12:00 PM | 23 Feb,2023 | Documentor fabricated a gantt chart that includes the programs implementation steps and
Abdulrahman | FR campus, N Block | 9:00 AM - 12:00 PM | 23 Feb,2023 | the research, also the gantt chart includes the planning stages.
Taha | FR campus, N Block | 9:00 AM - 12:00 PM | 23 Feb,2023 | we attempted to run the program on the Lab machine in N block but it didn’t have the specifications required.
taha and assers task was to figure out where we can run and test our system.
(Meeting 6) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk assesment
Participants | Location | Time | Date | Abdulrahman the group leader assigned taha and asser to debug the code and figure out its | Asser | Programmer | Asser | Task achieved | no risk
|  |  |  | issues. | Taha | Programmer | Taha | Task achieved
Yousef | FR campus, N Block | 3:10 PM - 6:00PM | 27 Feb,2023 | Meshina and yousef were assigned to finish up the gantt chart and move onto the design and testing. | Meshina | Documentor | Meshina | Task achieved
Asser | FR campus, N Block | 3:10 PM - 6:00PM | 27 Feb,2023 | We asked around if there was a super computer on campus we can use to run our system and sent an email | Abdulrahman | Group Leader / Research | Abdulrahman | Group leader
Meshina | FR campus, N Block | 3:10 PM - 6:00PM | 27 Feb,2023 | to the IT department and are waiting for a response. | Yousef | Research | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 3:10 PM - 6:00PM | 27 Feb,2023 | taha and asser were assigned to consider other routes to implement our object detection program
Taha | FR campus, N Block | 3:10 PM - 6:00PM | 27 Feb,2023
(Meeting 7) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk assesment
Participants | Location | Time | Date | Yousef was assigned to calculate the risk and help asser implement the design and test plan | Asser | Programmer | Asser | Task achieved | Rating = [ ∑i=1..4 [(wi*nfi)]/Nf ] * [ ∑i=1..4 [(wi*nsi)]/Ns ]
|  |  |  | Meshina was asked to continue working on the rest of the report no goal was set | Taha | Programmer | Taha | Couldn’t attend | nfi =1, Nf =3 , nsi = 2, Ns =4, wi=3
Yousef | FR campus, N Block | 9:40 AM - 12:00AM | 2 Mar,2023 | taha and abdulrahman werent able to make it to class today | Meshina | Documentor | Meshina | no task given | [(2*1)/3] = 0.67, [(2*2)/4 =1
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 2 Mar,2023 |  | Abdulrahman | Group Leader / Research | Abdulrahman | Couldn’t attend | Rating = (0.67 *1) = 0.67
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 2 Mar,2023 |  | Yousef | Research | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 2 Mar,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 2 Mar,2023
(Meeting 8) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | By this time we were practically done with the program itself and began putting all of our efforts into the | Asser | Group Leader | Asser | Ongoing till next week | No Risk
|  |  |  | report and presentation. | Taha | Documentor | Taha | Ongoing till next week
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 06 Mar,2023 | Meshina was asked to work on the responsibility matrix | Meshina | Programmer | Meshina | Ongoing till next week
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 06 Mar,2023 | Taha was asked to work and finish off the design and testing | Abdulrahman | Research | Abdulrahman | Ongoing till next week
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 06 Mar,2023 | Abdulrahman had been assigned to go over the initial files we had created in the beginning about the | Yousef | Programmer | Yousef | Ongoing till next week
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 06 Mar,2023 | functional and non functional requirements.
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 06 Mar,2023 | Yousef worked on the evaluations and lessons learned
(Meeting 9) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Same tasks as previous session | Asser | Group Leader | Asser | Task achieved | No Risk
[5 empty] | Taha | Documentor | Taha | Task achieved
Yousef | FR campus, N Block | 9:00 pm - 12:00pm | 09 Mar,2023 |  | Meshina | Programmer | Meshina | Task achieved
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 09 Mar,2023 |  | Abdulrahman | Research | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 09 Mar,2023 |  | Yousef | Programmer | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 09 Mar,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 09 Mar,2023
(Meeting 10) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Taha was performing the final touches on the design and testing section and asser was assisting | Asser | Programmer | Asser | Task achieved | No Risk
|  |  |  | Meshina and Yousef worked on the evaluations and lessons learned | Taha | Programmer | Taha | Task achieved
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 13 Mar,2023 | Abdulrahman was structuring the report | Meshina | Research | Meshina | Task achieved
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 13 Mar,2023 |  | Abdulrahman | Documentor | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 13 Mar,2023 |  | Yousef | Group Leader | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 13 Mar,2023
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 13 Mar,2023
(Meeting 11) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Taha's task was to go over the presesntation requirements and create a summarized form of the | Asser | Programmer | Asser | Task achieved | No Risk
|  |  |  | specification | Taha | Programmer | Taha | Task achieved
Yousef | FR campus, N Block | 9:00 pm - 12:00pm | 16 Mar,2023 | Meshina was assigned to research points we can write about in the evaluations and lessons learned | Meshina | Research | Meshina | Task achieved
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 16 Mar,2023 | Asser and Yousef and Abdulrahman were working on the implementation and testing section in the report | Abdulrahman | Documentor | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 16 Mar,2023 |  | Yousef | Group Leader | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 16 Mar,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 16 Mar,2023
(Meeting 12) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | We put aside the presentation for now | Asser | Research | Asser | Ongoing till next session | No Risk
|  |  |  | Meshina spent her time on the minutes and later updated the gannt chart | Taha | Documentor | Taha | Ongoing till next session
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 20 Mar,2023 | taha and yousef were assigned to continue working on the implementation and testing by making the code | Meshina | Group Leader | Meshina | Task achieved
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 20 Mar,2023 | presentable to insert the code snippets into the report | Abdulrahman | Programmer | Abdulrahman | On going till next session
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 20 Mar,2023 | Asser was assigned to work on the introduction | Yousef | Programmer | Yousef | On going till next session
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 20 Mar,2023 | Abdulrahman was asked to draft up a requirements sections.
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 20 Mar,2023
(Meeting 13) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Same as previous week | Asser | Research | Asser | Task achieved | No Risk
[5 empty] | Taha | Documentor | Taha | Task achieved
Yousef | FR campus, N Block | 9:00 pm - 12:00pm | 23 Mar,2023 |  | Meshina | Group Leader | Meshina | Task achieved
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 23 Mar,2023 |  | Abdulrahman | Programmer | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 23 Mar,2023 |  | Yousef | Programmer | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 23 Mar,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 23 Mar,2023
(Meeting 14) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | No tasks were assigned the group just went over the previous work we have done to make sure there were | Asser | Programmer | Asser | Task achieved | No Risk
|  |  |  | no mistakes. | Taha | Group Leader | Taha | Task achieved
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 27 Mar,2023 |  | Meshina | Documentor | Meshina | Task achieved
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 27 Mar,2023 |  | Abdulrahman | Research | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 27 Mar,2023 |  | Yousef | Programmer | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 27 Mar,2023
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 27 Mar,2023
(Meeting 15) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Yousef and asser were assigned with going over the report and make sure every seciton is the | Asser | Programmer | Asser | Task achieved | No Risk
|  |  |  | correct word count | Taha | Group Leader | Taha | Task achieved
Yousef | FR campus, N Block | 9:00 pm - 12:00pm | 30 Mar,2023 | Taha was adding the contribution percentages | Meshina | Documentor | Meshina | Task achieved
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 30 Mar,2023 | Meshina and Abdulrahman found grammatical and spelling mistakes in the report and fixed them | Abdulrahman | Research | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 30 Mar,2023 |  | Yousef | Programmer | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 30 Mar,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 30 Mar,2023
(Meeting 16) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Everyone was focused on finishing the rest of the sections | Asser | Research | Asser | no tasks | No Risk
|  |  |  | Also included a contents table | Taha | Documentor | Taha | no tasks
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 17 Apr,2023 |  | Meshina | Programmer | Meshina | no tasks
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 17 Apr,2023 |  | Abdulrahman | Programmer | Abdulrahman | no tasks
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 17 Apr,2023 |  | Yousef | Group Leader | Yousef | no tasks
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 17 Apr,2023
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 17 Apr,2023
(Meeting 17) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | Taha, Meshina and Yousef started working on the powerpoint and agreed on a theme, font and color way | Asser | Research | Asser | Task achieved | No Risk
|  |  |  | with the rest of the group | Taha | Documentor | Taha | Task achieved
Yousef | FR campus, N Block | 9:00 pm - 12:00pm | 20 Apr,2023 | Asser was assigned to research templates and other innovative ways we can improve our powerpoint | Meshina | Programmer | Meshina | Task achieved
Asser | FR campus, N Block | 9:40 AM - 12:00AM | 20 Apr,2023 | Abdulrahman added comments to the code | Abdulrahman | Programmer | Abdulrahman | Task achieved
Meshina | FR campus, N Block | 9:40 AM - 12:00AM | 20 Apr,2023 |  | Yousef | Group Leader | Yousef | Task achieved
Abdulrahman | FR campus, N Block | 9:40 AM - 12:00AM | 20 Apr,2023
Taha | FR campus, N Block | 9:40 AM - 12:00AM | 20 Apr,2023
(Meeting 18) |  |  |  | Topics Discussed | Group Roles |  | Tasks Achieved |  | Risk Assessment
Participants | Location | Time | Date | We made some last minute changes to the report and proof read it | Asser | Group Leader/ Programmer | Asser | no tasks | No Risk
|  |  |  | Also spent some time developing the presentation and getting ready for presentation day | Taha | Programmer | Taha | no tasks
Yousef | FR campus, N Block | 15:30 AM - 12:30PM | 24 Apr,2023 |  | Meshina | Documentor | Meshina | no tasks
Asser | FR campus, N Block | 15:30 AM - 12:30PM | 24 Apr,2023 |  | Abdulrahman | Research | Abdulrahman | no tasks
Meshina | FR campus, N Block | 15:30 AM - 12:30PM | 24 Apr,2023 |  | Yousef | Research | Yousef | no tasks
Abdulrahman | FR campus, N Block | 15:30 AM - 12:30PM | 24 Apr,2023
Taha | FR campus, N Block | 15:30 AM - 12:30PM | 24 Apr,2023